## Tasks and Timeline
Sauce & Spoon Project Plan
Milestones and Tasks | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone 1. Project Initiation
1.1 Shipping and receiving the tablets | Delayed by a few weeks because of the halt in supply line |  |  | a few weeks
1.2 Schedule an electrician | On track |  |  | 1 Day
1.3 Connect the Sauce & Spoon marketing team with Terrific Tablets for branding | Possible without any risk |  |  | 1 Week
1.4 Complete the wiring for both locations | It's the first time for wiring activity, it might take more time and will have some issues |  |  | 4 days
1.5 Install tablets in the bar areas at the Downtown and North restaurant locations | The delay will halt this process |  |  | 2 Days
Milestone 2. Test Tablet Features
2.1 Add a reservation booking feature to the tablets | Need to re-estimate |  |  | 1 Day
2.2 Upload the menu items and coupon values as a tablet feature | It's upto how Carter will handle the situation |  |  | 1 week
2.3 Sync up the tablet software with our POS system | It's highly unlikely that there would be any issue |  |  | 2 days
2.4 Test out reservation systems | To be decided |  |  | 1 Day
2.5 Integrated tablet software with their POS system | The systems are never upgraded so there will be certain issues |  |  | 2 days
2.6 Run tests on the tablet software | To be decided |  |  | 1 Day
Milestone 3. Training
3.1 Train the staff to update the menu | After the alternate tablet arrangement is done |  |  | 3 Days
3.2 Train general managers how to enter payroll | After the alternate tablet arrangement is done |  |  | 1 Week
3.3 Include payment security talking points in waitstaff training | After the alternate tablet arrangement is done |  |  | 1 Week
Milestone 4. Launch
4.1 Create a launch day plan: staffing, troubleshooting, etc. | To be decided |  |  | 1 Month
4.2 Create a procedure for securing tablets at the end of the night (at the table or in a safe) | Need to re-estimate |  |  | 1 Day
4.3 Create messaging about payment portal security to display on the tablets | Would require new dates |  |  | 1 Week
4.4 Implement a post-dining survey to assess customer satisfaction | Would require new dates |  |  | 1 Week
4.5 Collect the data and use it for customizing the product mix | Would require new dates |  |  | 1 Month
4.6 Check for alternate tablet arrangement | To be decided |  |  | 1 Week

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Shipping and receiving the tablets | Delayed by a few weeks because of the halt in supply line | a few weeks | a few weeks | 1 month | 2 months | L
Upload the menu items and coupon values as a tablet feature | It's upto how Carter will handle the situation | a few hours | a few hours | a day | a week | M
Sync up the tablet software with our POS system | It's highly unlikely that there would be any issue | a few hours | a few hours | a day | a week | H
Complete the wiring for both locations | It's the first time for wiring activity, it might take more time and will have some issues | 2 days | 2 days | 4 days | a week | M
Integrated tablet software with their POS system | The systems are never upgraded so there will be certain issues | 2 days | 2 days | 4 days | a week | L

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Order placing experience | The amount of time between placing an order and delivering it to the table | Is the order placing and delivery time reduced by 30 minutes ? | a good average is eight minutes for appetizers and 12-15 minutes for entrees | FALSE | https://www.coursera.org/learn/applying-project-management/resources/LGRfx
Checkout process | one-minute checkout time and ensure the checkout process is seamless and easy to navigate | How happy the customers are with the tablet checkout process? | Measure customer satisfaction rate by asking them a simple question afer checkout process | FALSE
Software quality | aim for 98% order accuracy in cutting down on incorrect orders | How accurate are the orders placed by our customers? | Order placing accuracy is meeting expectations | FALSE | Customer Satisfaction
| less than 5% of customers who use the tablets to report technical issues each week | What is the percent of issues reported by our customers in this month? | Reduce the number of order placing issues | FALSE | Are customers receiving the correct orders?
|  |  |  | FALSE | Are customers having a better dining experience with the tablets?
|  |  |  | FALSE | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend
|  |  |  | FALSE | Guests with shorter wait times report wanting to return 20% more often than those with longer wait times
FALSE
|  |  |  | FALSE | Tablet Ease of Use
|  |  |  | FALSE | Do all the tablets work as expected?
|  |  |  | FALSE | How quickly are customers learning how to navigate the tablets?
FALSE
|  |  |  | FALSE | Tablets functions
|  |  |  | FALSE | Waitstaff can log into their tablet accounts on the first try
|  |  |  | FALSE | 98% of customers who use tablets receive the correct order
FALSE
FALSE
|  |  |  | FALSE | Survey question types
|  |  |  | FALSE | “Does the new feature improve user experience and satisfaction with our app? Which of the following survey questions can help you answer this evaluation question?
FALSE
|  |  |  | FALSE | When did you first hear about this feature?
|  |  |  | FALSE | Did you encounter any technical difficulties while using this feature?
|  |  |  | FALSE | On a scale of 1–5, where 1 is “very easy” and 5 is “not at all easy,” how easy is this feature to use?
|  |  |  | FALSE | Would you recommend this feature to a friend?
|  |  |  | FALSE | Do you know which other banking apps include this feature?
FALSE
FALSE
|  |  |  | FALSE | “How satisfied are our customers with the new recipes?” Which of the following survey questions would be most useful to answer the evaluation question?
FALSE
|  |  |  | FALSE | Do we offer enough high-protein options to fit your active lifestyle?
|  |  |  | FALSE | How often do you use our meal kits?
|  |  |  | FALSE | Why is our best-selling pasta primavera your favorite recipe?
|  |  |  | FALSE | How many of our new recipes would you make again?
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
The amount of time between placing an order and delivering it to the table | Is the order placing and delivery time reduced by 30 minutes ? | a good average is eight minutes for appetizers and 12-15 minutes for entrees | What was the food delivery time after your placed orders on tablets? | Multiple choice | 15 mins | 20 mins | 30 mins | More than 40 minutes
one-minute checkout time and ensure the checkout process is seamless and easy to navigate | How happy the customers are with the tablet checkout process? | Measure customer satisfaction rate by asking them a simple question afer checkout process | Did you like the time of food delivery on table? | Yes/No | Yes | No
aim for 98% order accuracy in cutting down on incorrect orders | How accurate are the orders placed by our customers? | Order placing accuracy is meeting expectations | Was the food delivery time on table better than other restaurants you visit? | Scaled | Yes | No | Somewhat | Needs improvement | Not good
less than 5% of customers who use the tablets to report technical issues each week | What is the percent of issues reported by our customers in this month? | Reduce the number of order placing issues | The checkout process didn't have any issue? | True/False | Yes | No
|  |  | How long did your dinner take tonight? | Open-ended | Open-ended
|  |  | Did you receive the same food that you ordered on your tabletop tablet? | Multiple choice | Yes | No | Some items were wrong
|  |  | What items you ordered were served with wrong items? (what was order) (what was served instead) | Open-ended | Open-ended
|  |  | Did the tablet application work well during your entire dining experience? | Yes/No | Yes | No
|  |  | The food was served within 30 minutes after placing an order? | True/False | TRUE | FALSE
|  |  | Did you face any challenge while processing the payment with the application or your bank? | Yes/No | Yes | No
|  |  | Were there any challenges you faced while dealing with the application? Please specify. | Scaled | Some challenges | No challenges | Lot of challenges
|  |  | How was your overall experience with the tabletop tablets? | Open-ended | Open-ended
|  |  | Did your dinner take less time than the last time you visited? | Yes/No | Yes | No
|  |  | What other payment options would you like us to add in our application? | Open-ended | Open-ended